## Sheet1
TaskNo | Level1 | Level2 Brakdown | Level3 Brakdown | Owner | Priority | Result
1 | Specification | GUI Design |  |  | High | Design document
2 |  | Support Command | Create Table |  | High | Command list (Format,Usage)
3 |  |  | Delete Table |  | Low
4 |  |  | Create Fields |  | High
5 |  |  | Change Fields |  | Low
6 |  |  | Delete Fields |  | Low
7 |  |  | Add Records |  | High
8 |  |  | Update Records |  | High
9 |  |  | Delete Records |  | High
10 |  |  | Select |  | High
11 |  |  | Where |  | High
12 |  |  | Order |  | High
13 |  |  | Like |  | High
14 |  | Support Data Type | String
Date
Number
15
16 |  | DB File Format | Row recognition | Park | High | Format Description
17 |  |  | Column recognition | Park | High
18
19
20 | Command Fetch | Extract words |  | Matt | High
21 |  | Find Command |  | Matt | High
22 |  | Find target |  | Matt | High
23 |  | Find Condition |  | Matt | High
24 |  | Interprete Command |  | Matt | High
25 |  | Connect Event Handler |  | Matt | High
26 |  | Error Handling |  | Matt | High
27 | File Handling | Create File |  | Park |  | Method Specification Parameters, Return value
28 |  | Delete File |  | Park
29 |  | Add String |  | Park
30 |  | Delete String |  | Park
31 |  | Change column |  | Park
32 |  | Read String
33
34
| Algorithm | Sorting |  | Joy
|  | Searching |  | Alan
35 | Event Handler | Create Table |  | Ronnie |  | Update File
36 |  | Delete Table |  | Ronnie |  | Update File
37 |  | Create Fields |  | Ronnie |  | Update File
38 |  | Change Fields |  | Ronnie |  | Update File
39 |  | Delete Fields |  | Ronnie |  | Update File
40 |  | Add Records |  | Ronnie |  | Update File
41 |  | Update Records |  | Ronnie |  | Update File
42 |  | Delete Records |  | Ronnie |  | Update File
43 |  | Select |  | Ronnie |  | Show result on GUI
44 |  | Where |  | Ronnie |  | Update File / Show result on GUI
45 |  | Order |  | Ronnie |  | Show result on GUI
46 |  | Like |  | Ronnie |  | Update File / Show result on GUI
47
| GUI | CreateGUI |  | Joy
|  | GUI EventHandler |  | Joy